## Cover
StayNest — Master Project File
Hotel & Hospitality · PoD 4 · Batch 11 · INTDE26JFSR011
Project | StayNest — Hotel & Hospitality Management System
Domain | Travel & Hospitality
Tech Stack | Java Spring Boot 3 · MySQL 8.4 · React v18 · Bootstrap 5
Team | PoD 4 · 5 Associates
Interim Eval | 26–29 Jun 2026
React starts | 20 Jul 2026 (Wk 11)
Final Eval | 12–18 Aug 2026

## Timeline
StayNest — Week-by-Week Timeline · Batch 11 Timetable Verified
Wk | Dates | Sprint | Syllabus — from timetable | Project work | Milestone
Wk1 | 11–15 May | Sprint 0 | Refresher: HTML/CSS/JS, SQL, Java | Self-study
Wk2 | 18–22 May | Sprint 0→1 | Agile+Jira+Git · Sprint 1 Planning | GitHub repo+Jira+stories | Repo live
Wk3 | 25–29 May | Sprint 1 | DSA+Design Patterns+Spring Core+Maven | Spring Boot project · MySQL schema
Wk4 | 1–5 Jun | Sprint 1 | Spring Core+Maven · JPA+Hibernate starts | JPA entities · Repositories | DB done
Wk5 | 8–12 Jun | Sprint 1→2 | Spring Data JPA · REST starts · Sprint 1 Review | DTOs+Service · Sprint 1 demo | Sprint 1 complete
Wk6 | 15–19 Jun | Sprint 2 | Spring REST (full week) | All CRUD APIs · Postman | APIs done
Wk7 | 22–26 Jun | Sprint 2 | REST+Debugging · JUnit+Mockito · Interim starts | JUnit tests · Git commit | INTERIM EVAL 26 Jun
Wk8 | 29 Jun–3 Jul | Sprint 2→3 | Interim Eval · Microservices starts | Interim demo · Microservices theory | INTERIM EXAM 29 Jun
Wk9 | 6–10 Jul | Sprint 3 | Microservices+Docker | FE Phase 1: React setup · static pages
Wk10 | 13–17 Jul | Sprint 3→4 | Copilot+Node.js+TypeScript+Bootstrap · Sprint 3 Review | FE Phase 1: Bootstrap layouts · Sprint 3 demo | Sprint 3 complete
Wk11 | 20–24 Jul | Sprint 4 | Bootstrap 5+React v18 starts | FE Phase 2: React components · useState | React starts
Wk12 | 27–31 Jul | Sprint 4 | React v18 · Frontend Debugging | FE Phase 2: all module UIs done | FE Phase 2 done
Wk13 | 3–7 Aug | Sprint 4→5 | Code Quality+SonarQube+AWS DevOps | FE Phase 3: API integration | FE DEADLINE ~8 Aug
Wk14 | 10–14 Aug | Sprint 4→Final | AWS DevOps · Sprint 4 Review · Final Eval starts | Integration merge · demo rehearsal | FINAL EVAL 12 Aug
Wk15 | 17–18 Aug | Final | Final Eval+HackerRank | Full demo: Book→CheckIn→Folio→Checkout | FINAL 17–18 Aug

## Module Assignments
StayNest — Module Assignments · PoD 4
Emp ID | Associate | Backend Modules | Frontend Modules | Score
2507322 | Hitesh Paluri | Identity & Access Management | Login + Admin Console | 14
2507314 | Yadavalli Bhanu Sai Prakash | Room Inventory & Config + Revenue Analytics | Room Config UI + Analytics Dashboard | 25
2507350 | Jigeesha Anagani | Front Desk & Stay + Housekeeping | Front Desk Console + Housekeeping Dashboard | 27
2507318 | Sivaramakrishnan B | F&B & Ancillary + Notifications | F&B POS + Dining Reservations + Notifications | 27
2507349 | Suma Sindhura Asapu | Reservation & Booking Management | Guest Booking Portal + Reservation UI | 14

## BE-Stories-S1
StayNest Backend Stories ¦ Identity & Access Management
Hitesh Paluri · ID: 2507322 · Backend deadline: ~24 Jun · Interim: 26–29 Jun 2026
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 1 — Phase 1A: DB Schema · Wk3–4 · 25 May–5 Jun · Spring Core+Maven
IAM-001 | Wk3–4 · 25 May–5 Jun | User Story | As a developer, I want MySQL schema for User and AuditLog tables. |  | Backlog
|  | Sub-task |  | User: UserID(PK AUTO_INC), Name VARCHAR(100), Role ENUM('GUEST','FRONTDESK','HOUSEKEEPING','FBMANAGER','REVENUEMANAGER','ADMIN'), Email VARCHAR(150) UNIQUE, Phone VARCHAR(20), PropertyID INT, Status ENUM('ACTIVE','INACTIVE') DEFAULT 'ACTIVE' | Backlog
|  | Sub-task |  | AuditLog: AuditID(PK AUTO_INC), UserID INT REFERENCES User(UserID), Action VARCHAR(50), EntityType VARCHAR(50), Timestamp DATETIME DEFAULT NOW() | Backlog
|  | Sub-task |  | Seed 5 users (one per role) + 3 audit log entries · Verify in MySQL Workbench | Backlog
Sprint 1 — Phase 1B: JPA Entities+Repos+Service · Wk4–5 · 4–11 Jun · Spring Data JPA
IAM-002 | Wk4–5 · 4–11 Jun | User Story | As a developer, I want JPA Entities, Repositories, and Services for IAM. |  | Backlog
|  | Sub-task |  | Role enum: GUEST, FRONTDESK, HOUSEKEEPING, FBMANAGER, REVENUEMANAGER, ADMIN | Backlog
|  | Sub-task |  | User.java @Entity: all fields, @Enumerated role/status, Lombok @Data @Builder @NoArgsConstructor @AllArgsConstructor | Backlog
|  | Sub-task |  | AuditLog.java @Entity: userId(Integer), action, entityType, @CreationTimestamp timestamp, Lombok @Data @Builder | Backlog
|  | Sub-task |  | UserRepository: findByEmail(), findByStatus() · AuditLogRepository: findByUserId(), findByAction(), findByTimestampBetween(), Page<AuditLog> findAll(Pageable) | Backlog
|  | Sub-task |  | ResourceNotFoundException, BadRequestException, GlobalExceptionHandler in com.staynest.config | Backlog
|  | Sub-task |  | AuditLogService @Slf4j: logAction(userId,action,entityType,entityId) — SHARED method called by all modules after merge | Backlog
|  | Sub-task |  | UserService @Slf4j: createUser(BCrypt hash), getUserById(), getAllUsers(), updateUserStatus(), deleteUser(soft) | Backlog
|  | Sub-task |  | SecurityConfig with BCryptPasswordEncoder @Bean | Backlog
Sprint 2 — Phase 2: REST APIs · Wk6 · 15–19 Jun · Spring REST
IAM-003 | Wk6 · 15–19 Jun | User Story | As an Admin, I want REST APIs for User management and Login (JWT). |  | Backlog
|  | Sub-task |  | JwtUtil: generateToken(email,role 24h), validateToken(), extractEmail(), extractRole() — add jjwt 0.11.5 | Backlog
|  | Sub-task |  | JwtFilter extends OncePerRequestFilter — Bearer header validation, sets SecurityContext | Backlog
|  | Sub-task |  | SecurityConfig: permit /api/auth/**, /api/audit-logs POST; secure all others; CORS allow localhost:3000 | Backlog
|  | Sub-task |  | AuthController /api/auth/login: POST → {token,role,userId} or 401 | Backlog
|  | Sub-task |  | UserController /api/users: POST→201, GET→list, GET/{id}→200/404, PATCH/{id}?status, DELETE/{id}→204 | Backlog
|  | Sub-task |  | AuditLogController /api/audit-logs: GET(pageable+filters), POST(logAction internal) | Backlog
|  | Sub-task |  | Test in Postman · Save IAM_Collection.json | Backlog
Sprint 2 — Phase 3: JUnit Tests · Wk7 · 22–26 Jun · TDD/JUnit+SLF4J
IAM-004 | Wk7 · 22–26 Jun | User Story | As a developer, I want JUnit tests for UserService. |  | Backlog
|  | Sub-task |  | UserServiceTest: createUser_valid, duplicateEmail→exception, getUserById_valid, getUserById_invalid→exception, updateStatus | Backlog
|  | Sub-task |  | All 5 tests pass with mvn test · @Slf4j in UserService, AuditLogService | Backlog

## BE-Stories-S2
StayNest Backend Stories ¦ Room Inventory & Config + Revenue Analytics
Yadavalli Bhanu Sai Prakash · ID: 2507314 · Backend deadline: ~24 Jun · Interim: 26–29 Jun 2026
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 1 — Phase 1A: DB Schema · Wk3–4 · 25 May–5 Jun · Spring Core+Maven
RIC-001 | Wk3–4 · 25 May–5 Jun | User Story | As a developer, I want MySQL schema for RoomType, Room, RatePlan, and HospitalityReport. |  | Backlog
|  | Sub-task |  | RoomType: RoomTypeID(PK), Name ENUM('STANDARD','DELUXE','SUITE','VILLA'), BedConfiguration VARCHAR(100), MaxOccupancy INT, BaseRate DECIMAL(10,2), AmenitiesList TEXT, Status ENUM('ACTIVE','INACTIVE') DEFAULT 'ACTIVE' | Backlog
|  | Sub-task |  | Room: RoomID(PK), RoomNumber VARCHAR(10) UNIQUE, Floor INT, RoomTypeID INT REFERENCES RoomType(RoomTypeID), PropertyID INT, Status ENUM('AVAILABLE','OCCUPIED','CLEANING','MAINTENANCE','BLOCKED') DEFAULT 'AVAILABLE' | Backlog
|  | Sub-task |  | RatePlan: RatePlanID(PK), RoomTypeID INT REFERENCES RoomType(RoomTypeID), Name ENUM('RACK','CORPORATE','SEASONAL','PROMO'), PricePerNight DECIMAL(10,2), ValidFrom DATE, ValidTo DATE, MealPlanIncluded BOOLEAN DEFAULT FALSE, Status ENUM('ACTIVE','INACTIVE') DEFAULT 'ACTIVE' | Backlog
|  | Sub-task |  | HospitalityReport: ReportID(PK), Scope VARCHAR(50), Metrics TEXT, GeneratedDate DATETIME DEFAULT NOW() | Backlog
|  | Sub-task |  | Seed 3 room types, 6 rooms (2 per type), 3 rate plans, 2 reports · Verify in MySQL | Backlog
Sprint 1 — Phase 1B: JPA Entities+Repos+Service · Wk4–5 · 4–11 Jun · Spring Data JPA
RIC-002 | Wk4–5 · 4–11 Jun | User Story | As a developer, I want JPA Entities and Services for Room Inventory and Analytics. |  | Backlog
|  | Sub-task |  | RoomTypeName enum, RoomStatus enum, RatePlanName enum | Backlog
|  | Sub-task |  | RoomType.java @Entity: all fields, amenitiesList(String), @Enumerated name/status, Lombok @Data @Builder | Backlog
|  | Sub-task |  | Room.java @Entity: @ManyToOne @JoinColumn(name='RoomTypeID') roomType, roomNumber, floor, propertyId(Integer), @Enumerated status | Backlog
|  | Sub-task |  | RatePlan.java @Entity: @ManyToOne @JoinColumn(name='RoomTypeID') roomType, @Enumerated name, pricePerNight, validFrom, validTo, mealPlanIncluded, @Enumerated status | Backlog
|  | Sub-task |  | HospitalityReport.java @Entity: scope, metrics(String), @CreationTimestamp generatedDate | Backlog
|  | Sub-task |  | RoomTypeRepository: findByStatus() · RoomRepository: findByStatus(), findByRoomType_RoomTypeId(), findByFloor() | Backlog
|  | Sub-task |  | RatePlanRepository: findByRoomType_RoomTypeId(), findByStatus(), findActiveByRoomTypeId(Integer,LocalDate) | Backlog
|  | Sub-task |  | HospitalityReportRepository: findByScope() | Backlog
|  | Sub-task |  | RoomTypeService @Slf4j: createRoomType(), getAllRoomTypes(), updateStatus() | Backlog
|  | Sub-task |  | RoomService @Slf4j: addRoom(), getRoomsByStatus(), getRoomsByType(), updateRoomStatus() | Backlog
|  | Sub-task |  | RatePlanService @Slf4j: createRatePlan(), getActivePlansForRoomType(roomTypeId,date), updateStatus() | Backlog
|  | Sub-task |  | HospitalityReportService @Slf4j: generateReport(scope), getAllReports(), getReportById() | Backlog
Sprint 2 — Phase 2: REST APIs · Wk6 · 15–19 Jun · Spring REST
RIC-003 | Wk6 · 15–19 Jun | User Story | As a Hotel Admin, I want REST APIs for Room Inventory and Analytics. |  | Backlog
|  | Sub-task |  | RoomTypeController /api/room-types: POST→201, GET→list, GET/{id}→200/404, PATCH/{id}/status | Backlog
|  | Sub-task |  | RoomController /api/rooms: POST→201 (validate roomTypeId), GET→list(?status=,?roomTypeId=), GET/{id}, PATCH/{id}/status | Backlog
|  | Sub-task |  | RatePlanController /api/rate-plans: POST→201, GET?roomTypeId=&date=, GET/{id}, PATCH/{id}/status | Backlog
|  | Sub-task |  | HospitalityReportController /api/hospitality-reports: POST?scope=→201, GET→list, GET/{id}, GET/summary | Backlog
|  | Sub-task |  | GET /api/rooms/available?checkIn=&checkOut= → list of AVAILABLE rooms for date range | Backlog
|  | Sub-task |  | Save RIC_HAR_Collection.json | Backlog
Sprint 2 — Phase 3: JUnit Tests · Wk7 · 22–26 Jun · TDD/JUnit+SLF4J
RIC-004 | Wk7 · 22–26 Jun | User Story | As a developer, I want JUnit tests for RoomService and RatePlanService. |  | Backlog
|  | Sub-task |  | RoomServiceTest: addRoom_validRoomType, addRoom_invalidRoomType→exception, updateRoomStatus_changes, getRoomsByStatus_returnsCorrect (4 tests) | Backlog
|  | Sub-task |  | RatePlanServiceTest: createRatePlan_valid, getActivePlansForDate_returnsCorrect (2 tests) | Backlog
|  | Sub-task |  | All 6 tests pass · @Slf4j in all services | Backlog

## BE-Stories-S3
StayNest Backend Stories ¦ Front Desk & Stay + Housekeeping
Jigeesha Anagani · ID: 2507350 · Backend deadline: ~24 Jun · Interim: 26–29 Jun 2026
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 1 — Phase 1A: DB Schema · Wk3–4 · 25 May–5 Jun · Spring Core+Maven
FDS-001 | Wk3–4 · 25 May–5 Jun | User Story | As a developer, I want MySQL schema for StayRecord, FolioItem, HousekeepingTask, and MaintenanceRequest. |  | Backlog
|  | Sub-task |  | StayRecord: StayID(PK), ReservationID INT UNIQUE, GuestID INT, AssignedRoomID INT, ActualCheckIn DATETIME, ActualCheckOut DATETIME, FolioBalance DECIMAL(10,2) DEFAULT 0.00, Status ENUM('ACTIVE','CHECKEDOUT') DEFAULT 'ACTIVE' | Backlog
|  | Sub-task |  | FolioItem: FolioItemID(PK), StayID INT REFERENCES StayRecord(StayID), ChargeType ENUM('ROOMRENT','FBCHARGE','LAUNDRY','SPA','TAX','DISCOUNT'), Description VARCHAR(200), Amount DECIMAL(10,2), PostedDate DATETIME DEFAULT NOW(), PostedBy INT | Backlog
|  | Sub-task |  | HousekeepingTask: TaskID(PK), RoomID INT, TaskType ENUM('CHECKOUT','STAYOVERSERVICE','TURNDOWN','DEEPCLEAN'), AssignedToID INT, AssignedDate DATE, CompletedAt DATETIME, Status ENUM('PENDING','INPROGRESS','DONE','SKIPPED') DEFAULT 'PENDING' | Backlog
|  | Sub-task |  | MaintenanceRequest: RequestID(PK), RoomID INT, ReportedBy INT, IssueDescription TEXT, Priority ENUM('LOW','MEDIUM','HIGH','URGENT'), RaisedDate DATE DEFAULT CURDATE(), ResolvedDate DATE, Status ENUM('OPEN','INPROGRESS','RESOLVED','DEFERRED') DEFAULT 'OPEN' | Backlog
|  | Sub-task |  | Seed 2 stay records + 4 folio items, 3 housekeeping tasks, 2 maintenance requests · Verify in MySQL | Backlog
Sprint 1 — Phase 1B: JPA Entities+Repos+Service · Wk4–5 · 4–11 Jun · Spring Data JPA
FDS-002 | Wk4–5 · 4–11 Jun | User Story | As a developer, I want JPA Entities and Services for Front Desk and Housekeeping. |  | Backlog
|  | Sub-task |  | StayStatus enum, ChargeType enum, TaskType enum, TaskStatus enum, MaintenancePriority enum, MaintenanceStatus enum | Backlog
|  | Sub-task |  | StayRecord.java @Entity: reservationId(Integer UQ), guestId(Integer), assignedRoomId(Integer), actualCheckIn/CheckOut as LocalDateTime, folioBalance(Double), @Enumerated status | Backlog
|  | Sub-task |  | FolioItem.java @Entity: @ManyToOne @JoinColumn(name='StayID') stayRecord, @Enumerated chargeType, description, amount, @CreationTimestamp postedDate, postedBy(Integer) | Backlog
|  | Sub-task |  | HousekeepingTask.java @Entity: roomId(Integer), @Enumerated taskType, assignedToId(Integer), assignedDate, completedAt as LocalDateTime, @Enumerated status | Backlog
|  | Sub-task |  | MaintenanceRequest.java @Entity: roomId(Integer), reportedBy(Integer), issueDescription, @Enumerated priority/status, raisedDate, resolvedDate | Backlog
|  | Sub-task |  | StayRecordRepository: findByGuestId(), findByStatus(), findByReservationId(Integer) | Backlog
|  | Sub-task |  | FolioItemRepository: findByStayRecord_StayId(Integer), findByChargeType() | Backlog
|  | Sub-task |  | HousekeepingTaskRepository: findByRoomId(), findByStatus(), findByAssignedToId() | Backlog
|  | Sub-task |  | MaintenanceRequestRepository: findByRoomId(), findByStatus(), findByPriority() | Backlog
|  | Sub-task |  | StayRecordService @Slf4j @Transactional: checkIn(reservationId,roomId)→create StayRecord+update Room status=OCCUPIED, postFolioItem(stayId,chargeType,amount), checkOut(stayId)→sum folio+set Status=CHECKEDOUT+Room=AVAILABLE | Backlog
|  | Sub-task |  | HousekeepingTaskService @Slf4j: createTask(), assignTask(taskId,staffId), updateTaskStatus(), getTasksByStatus() | Backlog
|  | Sub-task |  | MaintenanceRequestService @Slf4j: reportIssue(), updateStatus(), resolveRequest()→set RESOLVED+resolvedDate=today | Backlog
Sprint 2 — Phase 2: REST APIs · Wk6 · 15–19 Jun · Spring REST
FDS-003 | Wk6 · 15–19 Jun | User Story | As a Front Desk Agent, I want REST APIs for Check-in, Folio, and Housekeeping. |  | Backlog
|  | Sub-task |  | StayRecordController /api/stay-records: POST/checkin?reservationId=&roomId=→201, GET?guestId=, GET/{id}→200/404, POST/{id}/folio-items→addCharge()→201, GET/{id}/folio-items→list, POST/{id}/checkout→checkOut()→200 | Backlog
|  | Sub-task |  | HousekeepingTaskController /api/housekeeping-tasks: POST→201, GET?status=, GET?roomId=, PATCH/{id}/assign?staffId=, PATCH/{id}/status | Backlog
|  | Sub-task |  | MaintenanceRequestController /api/maintenance-requests: POST→201, GET?roomId=, GET?status=OPEN, PATCH/{id}/status, PATCH/{id}/resolve | Backlog
|  | Sub-task |  | Test full stay flow: check-in → post folio items → get running total → checkout · Save FDS_HKM_Collection.json | Backlog
Sprint 2 — Phase 3: JUnit Tests · Wk7 · 22–26 Jun · TDD/JUnit+SLF4J
FDS-004 | Wk7 · 22–26 Jun | User Story | As a developer, I want JUnit tests for StayRecordService and HousekeepingTaskService. |  | Backlog
|  | Sub-task |  | StayRecordServiceTest: checkIn_valid_createsStayAndUpdatesRoom, postFolioItem_addsToFolio, checkOut_setsStatusAndFreesRoom (3 tests) | Backlog
|  | Sub-task |  | HousekeepingTaskServiceTest: createTask_savedPending, updateTaskStatus_inprogressToDone (2 tests) | Backlog
|  | Sub-task |  | MaintenanceRequestServiceTest: reportIssue_savedOpen, resolveRequest_setsResolvedAndDate (2 tests) | Backlog
|  | Sub-task |  | All 7 tests pass · @Slf4j verified | Backlog

## BE-Stories-S4
StayNest Backend Stories ¦ F&B & Ancillary + Notifications
Sivaramakrishnan B · ID: 2507318 · Backend deadline: ~24 Jun · Interim: 26–29 Jun 2026
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 1 — Phase 1A: DB Schema · Wk3–4 · 25 May–5 Jun · Spring Core+Maven
FBM-001 | Wk3–4 · 25 May–5 Jun | User Story | As a developer, I want MySQL schema for MenuItem, FBOrder, DiningReservation, and Notification. |  | Backlog
|  | Sub-task |  | MenuItem: MenuItemID(PK), Name VARCHAR(150), Category ENUM('BREAKFAST','MAINCOURSE','BEVERAGE','DESSERT'), Price DECIMAL(10,2), IsAvailable BOOLEAN DEFAULT TRUE, DietaryTags VARCHAR(200) | Backlog
|  | Sub-task |  | FBOrder: OrderID(PK), StayID INT, TableNumber VARCHAR(20), OrderType ENUM('DINEIN','INROOMDINING','TAKEAWAY'), ItemsJSON TEXT, TotalAmount DECIMAL(10,2), OrderTime DATETIME DEFAULT NOW(), Status ENUM('PLACED','PREPARING','SERVED','BILLED','CANCELLED') DEFAULT 'PLACED' | Backlog
|  | Sub-task |  | DiningReservation: DiningResID(PK), GuestID INT, StayID INT, RestaurantOutlet VARCHAR(100), Date DATE, Time TIME, Covers INT, Status ENUM('CONFIRMED','SEATED','COMPLETED','CANCELLED','NOSHOW') DEFAULT 'CONFIRMED' | Backlog
|  | Sub-task |  | Notification: NotificationID(PK), UserID INT, Message TEXT, Category ENUM('RESERVATION','FRONTDESK','HOUSEKEEPING','FB','REVENUE'), Status ENUM('UNREAD','READ','DISMISSED') DEFAULT 'UNREAD', CreatedDate DATETIME DEFAULT NOW() | Backlog
|  | Sub-task |  | Seed 5 menu items (different categories), 3 orders, 2 dining reservations, 5 notifications · Verify in MySQL | Backlog
Sprint 1 — Phase 1B: JPA Entities+Repos+Service · Wk4–5 · 4–11 Jun · Spring Data JPA
FBM-002 | Wk4–5 · 4–11 Jun | User Story | As a developer, I want JPA Entities and Services for F&B and Notifications. |  | Backlog
|  | Sub-task |  | MenuCategory enum, OrderType enum, OrderStatus enum, DiningResStatus enum, NotificationCategory enum, NotificationStatus enum | Backlog
|  | Sub-task |  | MenuItem.java @Entity: name, @Enumerated category, price, isAvailable(Boolean), dietaryTags, Lombok @Data @Builder | Backlog
|  | Sub-task |  | FBOrder.java @Entity: stayId(Integer), tableNumber, @Enumerated orderType, itemsJson(String), totalAmount, @CreationTimestamp orderTime, @Enumerated status | Backlog
|  | Sub-task |  | DiningReservation.java @Entity: guestId/stayId as Integer, restaurantOutlet, date, time, covers, @Enumerated status | Backlog
|  | Sub-task |  | Notification.java @Entity: userId(Integer), @Enumerated category/status, @CreationTimestamp createdDate | Backlog
|  | Sub-task |  | MenuItemRepository: findByCategory(), findByIsAvailable(Boolean) | Backlog
|  | Sub-task |  | FBOrderRepository: findByStayId(Integer), findByStatus(), findByOrderType() | Backlog
|  | Sub-task |  | DiningReservationRepository: findByGuestId(), findByDate(LocalDate), findByStatus() | Backlog
|  | Sub-task |  | NotificationRepository: findByUserId(), findByUserIdAndStatus(), countByUserIdAndStatus() | Backlog
|  | Sub-task |  | MenuItemService @Slf4j: addMenuItem(), getAllMenuItems(), getByCategory(), updateAvailability(), updatePrice() | Backlog
|  | Sub-task |  | FBOrderService @Slf4j @Transactional: placeOrder()→calculate totalAmount from itemsJSON+menuPrices, updateOrderStatus(), getOrdersByStay(), cancelOrder(if PLACED only) | Backlog
|  | Sub-task |  | DiningReservationService @Slf4j: createReservation(), updateReservationStatus(), getReservationsByDate() | Backlog
|  | Sub-task |  | NotificationService @Slf4j: sendNotification(→UNREAD), getByUser(), markAsRead(), markAllAsRead()→count, getUnreadCount() | Backlog
Sprint 2 — Phase 2: REST APIs · Wk6 · 15–19 Jun · Spring REST
FBM-003 | Wk6 · 15–19 Jun | User Story | As an F&B Manager/Guest, I want REST APIs for F&B Management and Notifications. |  | Backlog
|  | Sub-task |  | MenuItemController /api/menu-items: POST→201, GET→list(?category=,?available=true), GET/{id}→200/404, PATCH/{id}/availability?value=, PATCH/{id}/price?value= | Backlog
|  | Sub-task |  | FBOrderController /api/fb-orders: POST→201, GET?stayId=, GET/{id}, PATCH/{id}/status, PATCH/{id}/cancel (400 if not PLACED) | Backlog
|  | Sub-task |  | DiningReservationController /api/dining-reservations: POST→201, GET?guestId=, GET?date=, PATCH/{id}/status | Backlog
|  | Sub-task |  | NotificationController /api/notifications: POST→201, GET/user/{userId}, GET/user/{userId}/unread, PATCH/{id}/read, PATCH/user/{userId}/read-all→{updated:N}, GET/user/{userId}/count→{unreadCount:N} | Backlog
|  | Sub-task |  | Save FBM_NAL_Collection.json · Test: add menu item → place order → update status to BILLED | Backlog
Sprint 2 — Phase 3: JUnit Tests · Wk7 · 22–26 Jun · TDD/JUnit+SLF4J
FBM-004 | Wk7 · 22–26 Jun | User Story | As a developer, I want JUnit tests for FBOrderService and NotificationService. |  | Backlog
|  | Sub-task |  | FBOrderServiceTest: placeOrder_calculatesCorrectTotal, cancelOrder_placed→cancelled, cancelOrder_serving→exception, updateOrderStatus_changes (4 tests) | Backlog
|  | Sub-task |  | NotificationServiceTest: sendNotification_unread, markAsRead_changes, getUnreadCount_correct, markAllAsRead_updatesAll (4 tests) | Backlog
|  | Sub-task |  | All 8 tests pass · @Slf4j in all services | Backlog

## BE-Stories-S5
StayNest Backend Stories ¦ Reservation & Booking Management
Suma Sindhura Asapu · ID: 2507349 · Backend deadline: ~24 Jun · Interim: 26–29 Jun 2026
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 1 — Phase 1A: DB Schema · Wk3–4 · 25 May–5 Jun · Spring Core+Maven
RBM-001 | Wk3–4 · 25 May–5 Jun | User Story | As a developer, I want MySQL schema for GuestProfile and Reservation tables. |  | Backlog
|  | Sub-task |  | GuestProfile: GuestID(PK AUTO_INC), Name VARCHAR(100), Email VARCHAR(150) UNIQUE, Phone VARCHAR(20), Nationality VARCHAR(50), IDDocumentType VARCHAR(50), IDNumber VARCHAR(100), PreferencesJSON TEXT, LoyaltyTier ENUM('NONE','SILVER','GOLD','PLATINUM') DEFAULT 'NONE', Status ENUM('ACTIVE','BLACKLISTED') DEFAULT 'ACTIVE' | Backlog
|  | Sub-task |  | Reservation: ReservationID(PK AUTO_INC), GuestID INT REFERENCES GuestProfile(GuestID), RoomTypeID INT, RatePlanID INT, CheckInDate DATE, CheckOutDate DATE, Nights INT, Adults INT, Children INT, TotalAmount DECIMAL(10,2), BookingChannel ENUM('DIRECT','PHONE','WALKIN') DEFAULT 'DIRECT', Status ENUM('CONFIRMED','CHECKEDIN','CHECKEDOUT','CANCELLED','NOSHOW') DEFAULT 'CONFIRMED' | Backlog
|  | Sub-task |  | Seed 3 guest profiles + 4 reservations (CONFIRMED/CHECKEDIN/CANCELLED/NOSHOW) · Verify in MySQL | Backlog
Sprint 1 — Phase 1B: JPA Entities+Repos+Service · Wk4–5 · 4–11 Jun · Spring Data JPA
RBM-002 | Wk4–5 · 4–11 Jun | User Story | As a developer, I want JPA Entities and Services for GuestProfile and Reservation. |  | Backlog
|  | Sub-task |  | LoyaltyTier enum (NONE,SILVER,GOLD,PLATINUM), GuestStatus enum, BookingChannel enum, ReservationStatus enum | Backlog
|  | Sub-task |  | GuestProfile.java @Entity: all fields, @Enumerated loyaltyTier/status, preferencesJson(String), Lombok @Data @Builder @NoArgsConstructor @AllArgsConstructor | Backlog
|  | Sub-task |  | Reservation.java @Entity: @ManyToOne @JoinColumn(name='GuestID') guest, roomTypeId/ratePlanId as Integer, checkInDate, checkOutDate, nights, adults, children, totalAmount, @Enumerated bookingChannel/status | Backlog
|  | Sub-task |  | GuestProfileRepository: findByEmail(), findByStatus(), findByLoyaltyTier() | Backlog
|  | Sub-task |  | ReservationRepository: findByGuest_GuestId(Integer), findByStatus(), findByCheckInDate(LocalDate), findByCheckInDateBetween() | Backlog
|  | Sub-task |  | GuestProfileService @Slf4j: createGuestProfile(), getGuestById(), getGuestByEmail(), updateLoyaltyTier(), blacklistGuest() | Backlog
|  | Sub-task |  | ReservationService @Slf4j @Transactional: createReservation() validate roomTypeId+ratePlanId exist (cross-module), cancelReservation() if CHECKEDIN→throw BadRequest, updateReservationStatus(), getReservationsByGuest(), getUpcomingReservations(date) | Backlog
Sprint 2 — Phase 2: REST APIs · Wk6 · 15–19 Jun · Spring REST
RBM-003 | Wk6 · 15–19 Jun | User Story | As a Front Desk Agent/Guest, I want REST APIs for Guest Profile and Reservation management. |  | Backlog
|  | Sub-task |  | GuestProfileController /api/guests: POST→201, GET→list(?loyaltyTier=), GET/{id}→200/404, GET/email/{email}, PATCH/{id}/loyalty?tier=, PATCH/{id}/blacklist | Backlog
|  | Sub-task |  | ReservationController /api/reservations: POST→201, GET?guestId=, GET?status=, GET/{id}→200/404, PATCH/{id}/cancel→200 or 400, PATCH/{id}/status, GET/upcoming?date= | Backlog
|  | Sub-task |  | Test: create guest → make reservation → cancel → verify cannot cancel if already CHECKEDIN · Save RBM_Collection.json | Backlog
Sprint 2 — Phase 3: JUnit Tests · Wk7 · 22–26 Jun · TDD/JUnit+SLF4J
RBM-004 | Wk7 · 22–26 Jun | User Story | As a developer, I want JUnit tests for GuestProfileService and ReservationService. |  | Backlog
|  | Sub-task |  | GuestProfileServiceTest: createProfile_valid, getByEmail_valid, duplicateEmail→exception (3 tests) | Backlog
|  | Sub-task |  | ReservationServiceTest: createReservation_valid, cancelReservation_confirmed→cancelled, cancelReservation_checkedIn→exception, getUpcomingReservations_returnsCorrect (4 tests) | Backlog
|  | Sub-task |  | All 7 tests pass · @Slf4j in both services | Backlog

## FE-Stories-S1
StayNest Frontend Stories ¦ IAM UI
Hitesh Paluri · ID: 2507322 · FE starts Wk9 (6 Jul) · FE deadline ~8 Aug · Final Eval 12–18 Aug
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 3+4 — Phase 1: Setup+Static Pages · Wk9–10 · 6–17 Jul · TypeScript+Bootstrap
IAM-FE-001 | Wk9–10 · 6–17 Jul | User Story | As a User, I want a Login page with static layout. |  | Backlog
|  | Sub-task |  | Create React app: npx create-react-app staynest-iam, npm install bootstrap react-router-dom axios | Backlog
|  | Sub-task |  | Create src/context/AuthContext.jsx with login/logout/useAuth — store user+token in localStorage key 'token' | Backlog
|  | Sub-task |  | Create src/services/api.js — axios instance, baseURL: http://localhost:8080/api, Authorization Bearer interceptor | Backlog
|  | Sub-task |  | Create src/pages/iam/LoginPage.jsx — Bootstrap card form, email+password fields (static, no API yet) | Backlog
|  | Sub-task |  | Create src/components/iam/Layout.jsx — Navbar (hotel branding) + role-based Sidebar + {children} | Backlog
|  | Sub-task |  | Add route /login → LoginPage in App.jsx · Verify npm start | Backlog
Sprint 4 — Phase 2: React Components+Forms · Wk11–12 · 20–31 Jul · React v18
IAM-FE-002 | Wk11–12 · 20–31 Jul | User Story | As an Admin, I want User Management with add/deactivate. |  | Backlog
|  | Sub-task |  | Create src/pages/iam/UserListPage.jsx — Bootstrap table, mock 5 staff users in useState | Backlog
|  | Sub-task |  | Columns: ID, Name, Role badge (color per role), Email, Property, Status badge, Actions | Backlog
|  | Sub-task |  | Search by name/email using .filter() on local state · Deactivate button updates state | Backlog
|  | Sub-task |  | Create src/components/iam/UserFormModal.jsx — controlled inputs, add to state on submit, validation | Backlog
Sprint 4+5 — Phase 3: API Integration · Wk13 · 3–8 Aug · Debugging+Code Quality
IAM-FE-003 | Wk13 · 3–8 Aug | User Story | As a User, I want Login and User Management connected to real APIs. |  | Backlog
|  | Sub-task |  | Create src/services/iam/userService.js: getUsers(), createUser(data), updateUserStatus(id,status) | Backlog
|  | Sub-task |  | LoginPage: POST /api/auth/login → store in AuthContext → redirect by role | Backlog
|  | Sub-task |  | UserListPage: useEffect → getUsers() replaces mock, loading spinner | Backlog
|  | Sub-task |  | Add ProtectedRoute.jsx — redirect to /login if no token · Test end-to-end | Backlog

## FE-Stories-S2
StayNest Frontend Stories ¦ Room Config + Analytics UI
Yadavalli Bhanu Sai Prakash · ID: 2507314 · FE starts Wk9 (6 Jul) · FE deadline ~8 Aug · Final Eval 12–18 Aug
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 3+4 — Phase 1: Setup+Static Pages · Wk9–10 · 6–17 Jul · TypeScript+Bootstrap
RIC-FE-001 | Wk9–10 · 6–17 Jul | User Story | As a developer, I want Room Inventory and Analytics pages with mock data. |  | Backlog
|  | Sub-task |  | Create src/pages/ric/RoomTypePage.jsx — Bootstrap cards (2×2 grid), mock 3 room types | Backlog
|  | Sub-task |  | Each card: name badge, bed config, max occupancy, base rate, amenities, status, Edit button | Backlog
|  | Sub-task |  | Create src/pages/ric/RoomListPage.jsx — Bootstrap table, mock 6 rooms, status badge (AVAILABLE=green, OCCUPIED=red, CLEANING=amber) | Backlog
|  | Sub-task |  | Create src/pages/ric/RatePlanPage.jsx — rate plans per room type (dropdown + table) | Backlog
|  | Sub-task |  | Create src/pages/har/AnalyticsDashboardPage.jsx — 4 KPI cards: Occupancy 78%, ADR ₹4500, RevPAR ₹3510, Guest Score 4.2/5 | Backlog
Sprint 4 — Phase 2: React Components+Forms · Wk11–12 · 20–31 Jul · React v18
RIC-FE-002 | Wk11–12 · 20–31 Jul | User Story | As a Hotel Admin, I want to configure room types, rooms, and rate plans. |  | Backlog
|  | Sub-task |  | Create src/components/ric/RoomTypeFormModal.jsx — form: Name select, BedConfig, MaxOccupancy, BaseRate, AmenitiesList | Backlog
|  | Sub-task |  | Create src/components/ric/RoomFormModal.jsx — form: RoomNumber, Floor, RoomType select, Property | Backlog
|  | Sub-task |  | Create src/components/ric/RatePlanFormModal.jsx — form: RoomType select, Name select, PricePerNight, ValidFrom, ValidTo, MealPlan toggle | Backlog
|  | Sub-task |  | Room status update: dropdown per row (AVAILABLE/CLEANING/MAINTENANCE/BLOCKED) | Backlog
|  | Sub-task |  | Analytics dashboard: hardcoded values with Bootstrap progress bars | Backlog
Sprint 4+5 — Phase 3: API Integration · Wk13 · 3–8 Aug · Debugging+Code Quality
RIC-FE-003 | Wk13 · 3–8 Aug | User Story | As a Hotel Admin, I want Room Config pages connected to real APIs. |  | Backlog
|  | Sub-task |  | Create src/services/ric/roomTypeService.js, roomService.js, ratePlanService.js | Backlog
|  | Sub-task |  | Create src/services/har/reportService.js: generateReport(), getSummary() | Backlog
|  | Sub-task |  | Replace all mock data with API calls + useEffect + loading/error states | Backlog
|  | Sub-task |  | GET /api/rooms/available?checkIn=&checkOut= powers the availability search on Reservation page | Backlog

## FE-Stories-S3
StayNest Frontend Stories ¦ Front Desk Console + Housekeeping Dashboard
Jigeesha Anagani · ID: 2507350 · FE starts Wk9 (6 Jul) · FE deadline ~8 Aug · Final Eval 12–18 Aug
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 3+4 — Phase 1: Setup+Static Pages · Wk9–10 · 6–17 Jul · TypeScript+Bootstrap
FDS-FE-001 | Wk9–10 · 6–17 Jul | User Story | As a developer, I want Front Desk and Housekeeping pages with mock data. |  | Backlog
|  | Sub-task |  | Create src/pages/fds/FrontDeskPage.jsx — two panels: Arrivals today + Departures today (mock 2 each) | Backlog
|  | Sub-task |  | Each arrival row: Guest Name, Room Type, Reservation ID, Check-In button | Backlog
|  | Sub-task |  | Create src/pages/fds/StayDetailPage.jsx — useParams stayId, running folio table + Add Charge button + Checkout button | Backlog
|  | Sub-task |  | Create src/pages/hkm/HousekeepingPage.jsx — task board (Kanban-style: PENDING/INPROGRESS/DONE columns) mock 3 tasks | Backlog
|  | Sub-task |  | Create src/pages/hkm/MaintenancePage.jsx — open maintenance requests table, priority badges | Backlog
Sprint 4 — Phase 2: React Components+Forms · Wk11–12 · 20–31 Jul · React v18
FDS-FE-002 | Wk11–12 · 20–31 Jul | User Story | As a Front Desk Agent, I want to check-in guests and manage folios. |  | Backlog
|  | Sub-task |  | Check-In button: opens RoomAssignModal (room number select from AVAILABLE rooms mock list), on confirm add to active stays state | Backlog
|  | Sub-task |  | Create src/components/fds/AddChargeModal.jsx — ChargeType select, Description, Amount — adds to folio state | Backlog
|  | Sub-task |  | Checkout button: window.confirm → mark stay as CHECKEDOUT in state, show total folio balance | Backlog
|  | Sub-task |  | Housekeeping task: click card → move to INPROGRESS/DONE (drag or button) | Backlog
|  | Sub-task |  | Maintenance: create request form modal, resolve button → RESOLVED in state | Backlog
Sprint 4+5 — Phase 3: API Integration · Wk13 · 3–8 Aug · Debugging+Code Quality
FDS-FE-003 | Wk13 · 3–8 Aug | User Story | As a Front Desk Agent, I want Front Desk and Housekeeping pages connected to real APIs. |  | Backlog
|  | Sub-task |  | Create src/services/fds/stayService.js: checkIn(), postFolioItem(), checkOut(), getFolioItems(stayId) | Backlog
|  | Sub-task |  | Create src/services/hkm/taskService.js: getTasks(), createTask(), updateTaskStatus() | Backlog
|  | Sub-task |  | Create src/services/hkm/maintenanceService.js: reportIssue(), getOpenRequests(), resolveRequest() | Backlog
|  | Sub-task |  | Replace mock data, add loading/error states · Test: check-in → add charges → checkout | Backlog

## FE-Stories-S4
StayNest Frontend Stories ¦ F&B POS + Dining + Notifications
Sivaramakrishnan B · ID: 2507318 · FE starts Wk9 (6 Jul) · FE deadline ~8 Aug · Final Eval 12–18 Aug
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 3+4 — Phase 1: Setup+Static Pages · Wk9–10 · 6–17 Jul · TypeScript+Bootstrap
FBM-FE-001 | Wk9–10 · 6–17 Jul | User Story | As a developer, I want F&B and Notification pages with mock data. |  | Backlog
|  | Sub-task |  | Create src/pages/fbm/MenuPage.jsx — Bootstrap card grid by category, mock 5 items (toggle Available) | Backlog
|  | Sub-task |  | Create src/pages/fbm/FBOrderPage.jsx — order entry: select items from menu + table/room number, submit | Backlog
|  | Sub-task |  | Active orders list: OrderID, Type badge, Items, Total, Status badge with update button | Backlog
|  | Sub-task |  | Create src/pages/fbm/DiningReservationPage.jsx — reservations table with date filter (mock 2 reservations) | Backlog
|  | Sub-task |  | Create src/components/nal/NotificationBell.jsx — bell icon + unread badge in Navbar (mock count=3) | Backlog
Sprint 4 — Phase 2: React Components+Forms · Wk11–12 · 20–31 Jul · React v18
FBM-FE-002 | Wk11–12 · 20–31 Jul | User Story | As an F&B Manager, I want to manage menus, take orders, and manage dining reservations. |  | Backlog
|  | Sub-task |  | Create src/components/fbm/MenuItemFormModal.jsx — Name, Category select, Price, DietaryTags, IsAvailable toggle | Backlog
|  | Sub-task |  | Order form: menu item checkboxes + quantity inputs → auto-calculate total | Backlog
|  | Sub-task |  | Order status buttons: PLACED→PREPARING→SERVED→BILLED (one step at a time) | Backlog
|  | Sub-task |  | Cancel order button: only works if PLACED, shows error if PREPARING+ | Backlog
|  | Sub-task |  | Dining reservation form modal: GuestID, Outlet, Date, Time, Covers | Backlog
|  | Sub-task |  | Create src/pages/nal/NotificationsPage.jsx — full list with category filter | Backlog
Sprint 4+5 — Phase 3: API Integration · Wk13 · 3–8 Aug · Debugging+Code Quality
FBM-FE-003 | Wk13 · 3–8 Aug | User Story | As an F&B Manager, I want F&B pages connected to real APIs. |  | Backlog
|  | Sub-task |  | Create src/services/fbm/menuService.js, orderService.js, diningService.js | Backlog
|  | Sub-task |  | Create src/services/nal/notificationService.js: getByUser(), markAsRead(), getUnreadCount() | Backlog
|  | Sub-task |  | NotificationBell: poll getUnreadCount() every 30s via setInterval (cleanup on unmount) | Backlog
|  | Sub-task |  | Replace mock data + loading/error states · Test: add menu item → place order → billing | Backlog

## FE-Stories-S5
StayNest Frontend Stories ¦ Guest Booking Portal + Reservation UI
Suma Sindhura Asapu · ID: 2507349 · FE starts Wk9 (6 Jul) · FE deadline ~8 Aug · Final Eval 12–18 Aug
Story ID | Week (timetable) | Type | User Story | Sub-task / Acceptance criteria | Status
Sprint 3+4 — Phase 1: Setup+Static Pages · Wk9–10 · 6–17 Jul · TypeScript+Bootstrap
RBM-FE-001 | Wk9–10 · 6–17 Jul | User Story | As a developer, I want Guest Profile and Reservation pages with mock data. |  | Backlog
|  | Sub-task |  | Create src/pages/rbm/BookingSearchPage.jsx — date range picker (CheckIn/CheckOut) + adults/children inputs | Backlog
|  | Sub-task |  | Mock search results: 3 room type cards with BaseRate, MaxOccupancy, Book Now button | Backlog
|  | Sub-task |  | Create src/pages/rbm/MyReservationsPage.jsx — Bootstrap table, mock 3 reservations | Backlog
|  | Sub-task |  | Columns: ID, Room Type, Check-In, Check-Out, Nights, Total, Status badge, Cancel button | Backlog
|  | Sub-task |  | Create src/pages/rbm/GuestProfilePage.jsx — profile card: name, email, loyalty tier badge, edit form | Backlog
Sprint 4 — Phase 2: React Components+Forms · Wk11–12 · 20–31 Jul · React v18
RBM-FE-002 | Wk11–12 · 20–31 Jul | User Story | As a Guest, I want to create reservations and manage my profile. |  | Backlog
|  | Sub-task |  | Book Now button: opens BookingConfirmModal — shows room details, RatePlan select, Adults/Children, TotalAmount calc | Backlog
|  | Sub-task |  | On confirm: add to MyReservations state, show success toast | Backlog
|  | Sub-task |  | Cancel button: window.confirm → Status=CANCELLED in state (show error if not CONFIRMED) | Backlog
|  | Sub-task |  | Create src/components/rbm/GuestProfileFormModal.jsx — edit name, phone, nationality, preferences | Backlog
|  | Sub-task |  | Loyalty tier badge: color per tier (NONE=grey, SILVER=light, GOLD=amber, PLATINUM=purple) | Backlog
Sprint 4+5 — Phase 3: API Integration · Wk13 · 3–8 Aug · Debugging+Code Quality
RBM-FE-003 | Wk13 · 3–8 Aug | User Story | As a Guest, I want Booking pages connected to real APIs. |  | Backlog
|  | Sub-task |  | Create src/services/rbm/guestService.js: getGuestById(), updateProfile(), updateLoyaltyTier() | Backlog
|  | Sub-task |  | Create src/services/rbm/reservationService.js: createReservation(), getReservations(guestId), cancelReservation(id) | Backlog
|  | Sub-task |  | BookingSearchPage: GET /api/rooms/available?checkIn=&checkOut= for real availability | Backlog
|  | Sub-task |  | Replace mock data + loading/error states · Test: search → book → see in My Reservations → cancel | Backlog